## Project Tracking
Date | Second Sprint | Status
2023-05-22 | Sprint Planning (USs are scored, task distribution is made and the hours of the daily meetins are set )
2023-05-23 | Create a project in Jira and enter test cases and user stories
2023-05-24 | Creating framework, creating public repository on Github and adding other team members
2023-05-25 | Writing test codes
Making necessary updates in Jira. (Ticket or necessary corrections)
When the bug is found, this issue will be created and assigned to the relevant developer and sent to TODO.
After the BUGs found are fixed, those tests will be run again and it will be ensured that they are problem-free.
2023-06-02 | Demo Meeting will be held (Sprint Review Meeting)-After the demo, every team will set a Retro Meeting.

## Poll
TEAM 3
SPRINT 2
POLL
Name | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02
Sevilay Turkoglu
Sariye Yucel
Huriye Sever
Murat Sever
Nurettin Koca
Ibrahim Kavakli
Ersin Karapazarlioglu
Murat Korkmaz
Huseyin Emre Senol
Parking Lot
1 ->
Daily hours : 21.00 |  |  |  |  | 2 ->
3 ->

## Features
Second Sprint
Function | Tester | API User Story | DB User Story | Test Type | Main Tools | Framework | Tools
QA-TL | Sevilay Turkoglu | API_US02 * API_US07 * | DB_US05 * DB_US14 * DB_US23 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA-SM | Sariye Yucel | API_US01 * API_US06 * API_US38 | DB_US04 * DB_US13 * DB_US22 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA | Huriye Sever | API_US05 * API_US21 | DB_US01 * DB_US10 * DB_US19 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA | Murat Sever | API_US12 * API_US20 | DB_US02 * DB_US11 * DB_US20 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA | Nurettin Koca | API_US25 * API_US26 * | DB_US09 * DB_US18 * DB_US27 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA | Ibrahim Kavakli | API_US10 * API_US22 | DB_US03 * DB_US12 * DB_US21 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA | Ersin Karapazarlioglu | API_US04 * API_US11 * | DB_US06 * DB_US24 * DB_US15 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA | Murat Korkmaz | API_US03 * API_US16 * | DB_US08 * DB_US17 * DB_US26 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql
QA | Huseyin Emre Senol | API_US09 * API_US17 | DB_US07 * DB_US16 * DB_US25 | API+DB Testing | Java + Selenium | Cucumber | Jira-Xray /Git GitHub/Postman/MySql

## API Product Backlog(English)
API US
End Point | US_ID | Description | Acceptance Criteria | Priority | Point | Assigne | TEST TYPE
/api/opdList | API_US01 | As an administrator I should be able to reach to OPD List via API link . | To api/opdList endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " must be verified |  |  | Sariye | Backend (API)
api/opdList to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body lists content (id: of content with "1" The content with patient_name : "John Smith" and id:"23" patient_id : "16" ) must be verified .
/api/staffList | API_US02 | Staff via API link as an administrator List I should be able to reach . | /api/staffList to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " must be verified |  |  | Sevilay | Backend (API)
/api/staffList to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list content (id: content with "4" name:"Sansa ", surname :"Gomez", and employee_id:"9008" ) must be verified .
inside the response body list The content (id:"10" is the name:" Natasha ", surname :" Romanoff ", and employee_id:"9010" ) must be verified .
inside the response body list content (id: of content with "16" name:"April ", surname :"Clinton", and employee_id:"9020" ) must be verified .
/api/ipdList | API_US03 | IPD List via API connection as an administrator I should be able to reach . | /api/ipdList to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  | Murat Korkmaz | Backend (API)
/api/ipdList to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list content (id:"11" is the content patient_name:" Mukul singh ", patient_id:"16" ) should be verified .
inside the response body list content (id:"13" content patient_name:" Marsh Martin " is patient_id:"24" ) should be verified .
/api/visitorsPurposeList | API_US04 | Visitor via API connection as an administrator purpose List I should be able to reach . | /api/visitorsPurposeList to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  | Ersin | Backend (API)
/api/visitorsPurposeList to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list the content ( id:"19" is visitors_ purpose :" feridun bey", description :"bayram 123 111", created_at : "2023-04-12 08:34:56" ) must be verified .
inside the response body list content (id:"29" content visitors_ purpose :" special work ", description :" special word details ", created_at : "2023-05-18 17:00:26" ) should be verified .
/api/visitorsPurposeId | API_US05 | As an administrator, the user whose id is given over the API connection Visitor I should be able to access the Purpose information . | /api/visitorsPurposeId to your endpoint valid Status returned when sending a GET body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Huriye | Backend (API)
/api/visitorsPurposeId to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data (id) the code is 403 and the message information in the response body is " failed " must be verified
in the response body ( id,visitors _purpose,description,created_at ) must be validated .
/api/visitorsPurposeAdd | API_US06 | A new visitor via API link as an administrator purpose registration I want to be able to create . | /api/visitorsPurposeAdd to your endpoint valid authorization information and correct Status returned when sending a POST body containing data ( visitors_purpose , description ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Sariye | Backend (API)
/api/visitorsPurposeAdd to your endpoint invalid Status returned when sending a POST body containing authorization information or wrong data ( visitors_purpose , description ) the code is 403 and the message information in the response body is " failed " must be verified
via API new visitor to be created purpose your record via the created API should be verified .
/api/visitorsPurposeUpdate | API_US07 | link as an administrator registered to the system via visitor I should be able to update the purpose information . | /api/visitorsPurposeUpdate to your endpoint valid Status returned when sending a PATCH body containing authorization information and correct data (id, visitors_purpose , description ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Sevilay | Backend (API)
/api/visitorsPurposeUpdate to your endpoint invalid Status returned when sending a PATCH body containing authorization information or wrong data (id, visitors_purpose , description ) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body UpdateId info /api/visitorsPurposeUpdate patch sent to endpoint It is the same as the id information in the request body . should be verified .
Visitor to be updated via API purpose your record updated via API should be verified .
/api/visitorsPurposeDelete | API_US08 | API_US08 Visitor in the system via API connection as an administrator puss I should be able to deregister. | /api/visitorsPurposeDelete to your endpoint valid Status returned when sending a DELETE body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/visitorsPurposeDelete to your endpoint invalid Status returned when sending a DELETE body containing authorization information or wrong data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body DeletedId info /api/visitorsPurposeDelete delete sent to endpoint It is the same as the id information in the request body . should be verified .
Visitor to be deleted via API purpose your record deleted , via API should be verified .
/api/visitorsList | API_US09 | Visitor via API connection as an administrator List I should be able to reach . | /api/visitorsList to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  | Huseyin | Backend (API)
/api/visitorsList to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list content (id: of content with "38" source : "Online", purpose :" Improve local visibility for heallifehospital.com", name: " Mike Holmes", email : "no-replyAnnora@gmail.com " , date:"2023-05-16", created_at : "2023-05-15 21:24:47" ) must be verified .
/api/visitorsId | API_US10 | As an administrator, the user whose id is given over the API connection I should be able to access the visitor information . | /api/visitorsId to your endpoint valid Status returned when sending a GET body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Ibrahim | Backend (API)
/api/visitorsId to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data (id) the code is 403 and the message information in the response body is " failed " must be verified
in the response body (id, sources , purpose , name, email , contact , id_proof , visit_to , ipd_opd_staff_id , related_to , no_of_pepple , date , in_time , out_time , note , created_at ) should be verified .
/api/visitorsAdd | API_US11 | A new visitor via API link as an administrator registration I want to create . | /api/visitorsAdd to your endpoint valid Status returned when sending a POST body containing authorization information and correct data ( purpose , name , email , contact , id_proof , visit_to , ipd_opd_staff_id , related_to , no_of_pepple , date , in_time , out_time , note ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Ersin | Backend (API)
/api/visitorsAdd to your endpoint invalid Status returned when sending a POST body containing authorization information or incorrect data ( purpose , name , email , contact , id_proof , visit_to , ipd_opd_staff_id , related_to , no_of_pepple , date , in_time , out_time , note ) the code is 403 and the message information in the response body is " failed " must be verified
via API new visitor to be created your record created , via API should be verified .
/api/visitorsUpdate | API_US12 | Registered to the system via API connection as an administrator I should be able to update the visitor information . | /api/visitorsUpdate to your endpoint valid status returned when sending a PATCH body with authorization information and correct data (id, purpose , name, email , contact , id_proof , visit_to , ipd_opd_staff_id , releated_to , no_of_pepple , date , in_time , out_time , note ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Murat S | Backend (API)
/api/visitorsUpdate to your endpoint invalid status returned when sending a PATCH body containing authorization information or incorrect data (id, purpose , name, email , contact , id_proof , visit_to , ipd_opd_staff_id , releated_to , no_of_pepple , date , in_time , out_time , note ) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body UpdateId info /api/visitorsUpdate patch sent to endpoint It is the same as the id information in the request body . should be verified .
Visitor to be updated via API your record updated via API should be verified .
/api/visitorsDelete | API_US13 | Visitor in the system via API connection as an administrator I should be able to deregister. | /api/visitorsDelete to your endpoint valid Status returned when sending a DELETE body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/visitorsDelete to your endpoint invalid Status returned when sending a DELETE body containing authorization information or wrong data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body DeletedId info /api/visitorsDelete delete sent to endpoint It is the same as the id information in the request body . should be verified .
Visitor to be deleted via API your record deleted , via API should be verifiable .
/api/getBloodGroup | API_US14 | As an administrator, I should be able to access the blood group list registered in the system via API connection . | /api/getBloodGroup to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  |  | Backend (API)
/api/getBloodGroup to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list The content must be verified ( the content with id:"3" is name: "AB-", is_blood_group : "1", created_at : "2021-10-25 02:32:41" ) .
inside the response body list The content ( the content with id:"8" is name: "O+", is_blood_group : "1", created_at : "2021-10-25 02:33:28" ) must be verified .
/api/getBloodGroupById | API_US15 | As an administrator, I should be able to access the relevant blood data by entering the id over the API connection . | /api/getBloodGroupById to your endpoint valid Status returned when sending a GET body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/getBloodGroupById to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body The data( id, name, is_blood_group , created_at ) must be validated .
/api/addBloodGroup | API_US16 | link as an administrator I want to be able to create a new blood group through it . | /api/addBloodGroup to your endpoint valid Status returned when sending a POST body containing authorization information and correct data ( name,is _blood_group ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Murat K | Backend (API)
/api/addBloodGroup to your endpoint invalid Status returned when sending a POST body containing authorization information or wrong data ( name,is _blood_group ) the code is 403 and the message information in the response body is " failed " must be verified
via API of the new blood group record to be created created , via API should be verified .
/api/updateBloodGroup | API_US17 | As an administrator, I should be able to update the blood information registered in the system via the API connection . | /api/updateBloodGroup to your endpoint valid Status returned when sending a PATCH body containing authorization information and correct data (id, name,is _blood_group ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Huseyin | Backend (API)
/api/updateBloodGroup to your endpoint invalid Status returned when sending a PATCH body containing authorization information or wrong data (id, name,is _blood_group ) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body UpdateId info /api/updateBloodGroup patch sent to endpoint It is the same as the id information in the request body . should be verified .
blood group record desired to be updated via API via the updated API should be verified .
/api/deleteBloodGroup | API_US18 | As an administrator, I should be able to delete the blood group record in the system via the API link . | /api/deleteBloodGroup to your endpoint valid Status returned when sending a DELETE body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/deleteBloodGroup to your endpoint invalid Status returned when sending a DELETE body containing authorization information or wrong data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body DeleteId info /api/deleteBloodGroup delete sent to endpoint It is the same as the id information in the request body . should be verified .
record desired to be deleted from the API deleted , via API should be verified .
/api/getExpenseHead | API_US19 | As an administrator to hospital expenses via API connection I should be able to reach . | /api/getExpenseHead to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  |  | Backend (API)
/api/getExpenseHead to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response message information is " failed " must be verified
inside the response body list content (id: content with "5" exp_category : " Power Generator fuel Charge ", description : "They can utilise a variety of fuel options including natural gas , LPG and diesel .", is_active : " yes ", is_deleted : " no ", created_at : " 2021-10-29 01:35:42" ) must be verified .
inside the response body list content (id: content with "4" exp_category : "Telephone Bill", description : " Recently , some private insurance companies have has begun to share for patient-to-provider phone calls , especially when the calls are prolonged and when medical decisions are made _ nevertheless , you may be billed for the wholesale cost , or you may have to pay a co -pay.", is_active : " yes " , is_deleted : " no " , created_at : " 2021-10-29 01:36:02" ) should be verified .
/api/getExpenseHeadById | API_US20 | As an administrator, I should be able to access the relevant expenditure data by entering the id over the API connection . | /api/getExpenseHeadById to your endpoint valid Status returned when sending a GET body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Murat S | Backend (API)
/api/getExpenseHeadById to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data (id) the code is 403 and the message information in the response body is " failed " must be verified
in the response body (id, exp_category , description , is_active , is_deleted , created_at ) must be verified .
/api/addExpenseHead | API_US21 | As an administrator, I want to be able to create a new expense over the API connection . | /api/addExpenseHead to your endpoint valid Status returned when sending a POST body containing authorization information and correct data ( exp_category , description , is_active , is_deleted ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Huriye | Backend (API)
/api/addExpenseHead to your endpoint invalid Status returned when sending a POST body containing authorization information or wrong data ( exp_category , description , is_active , is_deleted ) the code is 403 and the message information in the response body is " failed " must be verified
via API of the new expense record to be created. created , via API should be verified .
/api/updateExpenseHead | API_US22 | Being able to update the expenditure information registered in the system via API connection as an administrator. I want.. | /api/updateExpenseHead to your endpoint valid Status returned when sending a PATCH body containing authorization information and correct data (id, exp_category , description , is_active , is_deleted ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Ibrahim | Backend (API)
/api/updateExpenseHead to your endpoint invalid Status returned when sending a PATCH body containing authorization information or wrong data (id, exp_category , description , is_active , is_deleted ) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body UpdateId info /api/updateExpenseHead patch sent to endpoint It is the same as the id information in the request body . should be verified .
Expense record to be updated via API updated via API should be verified .
/api/deleteExpenseHead | API_US23 | As an administrator, I should be able to delete the expense record in the system via the API connection . | /api/deleteExpenseHead to your endpoint valid Status returned when sending a DELETE body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/deleteExpenseHead to your endpoint invalid Status returned when sending a DELETE body containing authorization information or wrong data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body of deletedId info /api/deleteExpenseHead delete sent to endpoint It is the same as the id information in the request body . should be verified .
record to be deleted via API deleted , via API should be verified .
/api/getNotice | API_US24 | As an administrator I should be able to access announcements via API link . | /api/getNotice to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  |  | Backend (API)
/api/getNotice to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list content (id: of content with "37" type : " notice ", slug : "happy-30-march-medicine-day", url: " page /", title ": " Happy 30 March medicine Day ", date : "2023-03-30", description ": "<p>< img align =\" left \" src=\"https://qa.heallifehospital.com/uploads/gallery/media/2.jpg\" width =\"300\" xss =\" removed \"></p >\r\n\r\n<p>On March 30th, we celebrate the contribution and hard work of the doctors in our hospital on International Medicine day _ this day is a time to acknowledge the crucial role that medicine plays in improving health and saving lives .< /p>\r\n\r\n<p> Our theme for this year &#39;s celebration is \" Advancing Health Through Science and Technology \", highlighting the importance of investing in medical research and innovation . It is a day to appreciate the efforts of our healthcare professionals and researchers in developing innovative treatments and cures for various diseases .< /p>\r\n\r\n<p> We would like to take this opportunity to extend our gratitude to all the doctors in our hospital for their tireless work and dedication to providing the best resort to our patients . your compassion , expertise , and commitment to advancing the field of medicine do not go unnoticed .< /p>\r\n\r\n<p> Let &#39;s celebrate this day together and continue to support our healthcare professionals in their our efforts to improve the lives of those around us. happy March 30th Medicine Day !< /p>", is_active : " no ", that ) should be verified .
inside the response body list content (id: of content with "38" type : " notice ", slug : "from-the-harvard-university-cell-science-course-prof-dr-alexander-smith-will-attend-the-cell-science-panel-to-be-held-in -our-hospital-as-a-speaker", url: " page /", title ": " From the Harvard University Cell Science course _ prof. Dr. Alexander Smithwill attend the Cell Science panel to be held in our hospital as a speaker .", date:"2023-05-10 ",, is_active : " no " , it ) must be verified .
/api/getNoticeById | API_US25 | As an administrator, I should be able to access the relevant announcement data by entering the id over the API connection . | / api / getNoticeById to your endpoint valid Status returned when sending a GET body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Nurettin | Backend (API)
/ api / getNoticeById to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data (id) the code is 403 and the message information in the response body is " failed " must be verified
in the response body (id, type , slug , url, title , date , event_start , event_end , event_venue , description , is_active , created_at , meta_title , meta_description , meta_keyword , feature_image , publish_date , publish , sidebar . ) must be verified .
/api/addNotice | API_US26 | Register a new announcement via API link as an administrator I want to be able to create . | /api/addNotice to your endpoint valid Status returned when sending a POST body containing authorization information and correct data ( type , title , description , slug ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  | Nurettin | Backend (API)
/api/addNotice to your endpoint invalid Status returned when sending a POST body containing authorization information or incorrect data ( type , title , description , slug ) the code is 403 and the message information in the response body is " failed " must be verified
via API of the new announcement record to be created. created , via API should be verified .
/api/updateNotice | API_US27 | As an administrator, I should be able to update the announcement information registered to the system via the API connection . | /api/updateNotice to your endpoint valid Status returned when sending a PATCH body containing authorization information and correct data (id, type , title , description , slug ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/updateNotice to your endpoint invalid Status returned when sending a PATCH body containing authorization information or wrong data (id, type , title , description , slug ) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body updateId info /api/updateNotice patch sent to endpoint It is the same as the id information in the request body . should be verified .
record to be updated via API updated via API should be verified .
/api/deleteNotice | API_US28 | As an administrator, I should be able to delete the announcement record in the system via the API connection . | /api/deleteNotice to your endpoint valid Status returned when sending a DELETE body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/deleteNotice to your endpoint invalid Status returned when sending a DELETE body containing authorization information or wrong data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body DeleteId info /api/deleteNotice delete sent to endpoint It is the same as the id information in the request body . should be verified .
record to be deleted via API via the deleted API should be verified .
/api/getFindingCategory | API_US29 | Finding via API link as an administrator I should be able to access the category list . | /api/getFindingCategory to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  |  | Backend (API)
/api/getFindingCategory to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list content (id: of content with "1" category : "Fever", created_at : "2021-10-25 02:02:48" ) must be verified .
inside the response body list content (id: content with "2" category : " Typhidot ( or Widal Test)", created_at : "2021-10-25 02:03:35" ) should be verified .
inside the response body list content (id: content with "3" category : "Skin Problem", created_at : "2021-10-25 02:14:41" ) must be verified .
/api/getFindingCategoryById | API_US30 | As an administrator, enter the id over the API connection . I should be able to access the category data . | /api/getFindingCategoryById to your endpoint valid Status returned when sending a GET body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/getFindingCategoryById to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body The data( id, category , created_at ) must be validated .
/api/addFindingCategory | API_US31 | As an administrator, you can make a new finding via API connection . category registration I want to be able to create . | /api/addFindingCategory to your endpoint valid Status returned when sending a POST body containing authorization information and correct data ( category , created_at ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/ api / addFindingCategory to your endpoint invalid Status returned when sending a POST body containing authorization information or wrong data ( category , created_at ) the code is 403 and the message information in the response body is " failed " must be verified
via API new finding to be created category your record created , via API should be verified .
/api/updateFindingCategory | API_US32 | Registered to the system via API connection as an administrator finding out I should be able to update the category information . | /api/updateFindingCategory to your endpoint valid Status returned when sending a PATCH body containing authorization information and correct data ( id, category ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/updateFindingCategory to your endpoint invalid Status returned when sending a PATCH body containing authorization information or wrong data ( id, category ) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body UpdateId info /api/updateFindingCategory patch sent to endpoint It is the same as the id information in the request body . should be verified .
Findings to be updated via API category your record updated via API should be verified .
/api/deleteFindingCategory | API_US33 | Registered to the system via API connection as an administrator finding out category I should be able to deregister. | /api/deleteFindingCategory to your endpoint valid Status returned when sending a DELETE body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/deleteFindingCategory to your endpoint invalid Status returned when sending a DELETE body containing authorization information or wrong data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body of deletedId info /api/deleteFindingCategory delete sent to endpoint It is the same as the id information in the request body . should be verified .
Findings to be deleted via API category your record via the deleted API should be verified .
/api/getFinding | API_US34 | As an administrator I should be able to access the find list via the API link . | /api/getFinding to your endpoint valid a GET request with authorization information status when sent the code is 200 and the response the message information is " Success " should be verified . |  |  |  | Backend (API)
/api/getFinding to your endpoint invalid A GET Request with authorization information status when sent that the code is 403 and the response the message information is " failed " must be verified
inside the response body list content (name of content with id:"12" : " Refractive Errors .", description : "A refractive error is a lot common eye disorder . it occurs when the eye cannot clearly focus the images from the outside world . the result of refractive errors is blurred vision , which is sometimes so severe that it causes visual impairment ", finding_category_id : "6", created_at : "2021-10-25 02:20:29", category : " Eye Diseases ) should be verified .
inside the response body list content (id:"7" content name: " Rosacea .", description : " Rosacea ( roe -ZAY- she - uh ) is a common skin condition that causes blushing or flushing and visible blood vessels in your face _ it may also produce small , pus- filled bump _ these signs and symptoms may flare up for weeks to months and then go away for a while .", finding_category_id : "3", created_at : "2021-10-25 02:15:36", category : "Skin Problem" ) must be verified .
/api/getFindingById | API_US35 | As an administrator, I should be able to access the relevant finding data by entering the id over the API connection . | /api/getFindingById to your endpoint valid Status returned when sending a GET body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/getFindingById to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data (id) the code is 403 and the message information in the response body is " failed " must be verified
in the response body (id, name, description , finding_category_id , created_at , category ) must be validated .
/api/getFindingCategoryId | API_US36 | As an administrator, enter the id over the API connection . I should be able to access the category data . | /api/getFindingCategoryId to your endpoint valid Status returned when sending a GET body containing authorization information and correct data ( finding_category_id ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
api/getFindingCategoryId to your endpoint invalid Status returned when sending a GET body containing authorization information and invalid data( finding_category_id ) The message in the response body that the code is 403 information is " failed " must be verified
inside the response body list The data in its content (with id, name, description , finding_category_id , created_at information) must be verified .
/api/addFinding | API_US37 | As an administrator, you can make a new finding via API connection . registration I want to be able to create . | /api/addFinding to your endpoint valid Status returned when sending a POST body containing authorization information and correct data (name, description , finding_category_id ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/addFinding to your endpoint invalid Status returned when sending a POST body containing authorization information or incorrect data (name, description , finding_category_id ) the code is 403 and the message information in the response body is " failed " must be verified
via API new finding to be created your record created , via API should be verified .
/api/updateFinding | API_US38 | Registered to the system via API connection as an administrator I should be able to update the finding information . | /api/updateFinding to your endpoint valid Status returned when sending a PATCH body containing authorization information and correct data ( id,name ,description,finding_category_id ) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
|  |  | /api/updateFinding to your endpoint invalid Status returned when sending a PATCH body containing authorization information or wrong data ( id,name ,description,finding_category_id ) the code is 403 and the message information in the response body is " failed " must be verified |  |  | Sariye
inside the response body /api/updateFinding of updateId info patch sent to endpoint It is the same as the id information in the request body . should be verified .
Findings to be updated via API your record updated via API should be verified .
/api/deleteFinding | API_US39 | Registered to the system via API connection as an administrator finding out I should be able to deregister. | /api/deleteFinding to your endpoint valid Status returned when sending a DELETE body with authorization information and correct data (id) that the code is 200 and the message information in the response body is " Success " must be verified |  |  |  | Backend (API)
/api/deleteFinding to your endpoint invalid Status returned when sending a DELETE body containing authorization information or wrong data (id) the code is 403 and the message information in the response body is " failed " must be verified
inside the response body /api/deleteFinding of deletedId info delete sent to endpoint It is the same as the id information in the request body . should be verified .
Findings to be deleted via API your record via the deleted API should be verified .

## API Product Backlog(Turkish)
API US
End Point | US_ID | Description | Acceptance Criteria | Priority | Point | Assigne | TEST TYPE
| API_US01 | Bir yönetici olarak API baglantisi üzerinden OPD List'e erisebilmeliyim. | api/opdList endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali |  |  | Sariye | Backend (API)
api/opdList endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki lists icerigi (id:"1" olan icerigin patient_name: "John Smith" ve id:"23" olan icerigin patient_id: "16" oldugu) dogrulanmali.
/api/staffList | API_US02 | Bir yönetici olarak API baglantisi üzerinden Staff List'e erisebilmeliyim. | /api/staffList endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali |  |  | Sevilay | Backend (API)
/api/staffList endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"4" olan icerigin name:"Sansa", surname:"Gomez", ve employee_id:"9008" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"10" olan icerigin name:"Natasha", surname:" Romanoff", ve employee_id:"9010" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"16" olan icerigin name:"April", surname:"Clinton", ve employee_id:"9020" oldugu) dogrulanmali.
/api/ipdList | API_US03 | Bir yönetici olarak API baglantisi üzerinden IPD List'e erisebilmeliyim. | /api/ipdList endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  | Murat Korkmaz | Backend (API)
/api/ipdList endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"11" olan icerigin patient_name:"Mukul singh", patient_id:"16" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"13" olan icerigin patient_name:"Marsh Martin", patient_id:"24" oldugu) dogrulanmali.
/api/visitorsPurposeList | API_US04 | Bir yönetici olarak API baglantisi üzerinden Visitor Purpose List'e erisebilmeliyim. | /api/visitorsPurposeList endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  | Ersin | Backend (API)
/api/visitorsPurposeList endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"19" olan icerigin visitors_purpose:"feridun bey", description:"bayram 123 111", created_at: "2023-04-12 08:34:56" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"29" olan icerigin visitors_purpose:"special work", description:"special word details", created_at: "2023-05-18 17:00:26" oldugu) dogrulanmali.
/api/visitorsPurposeId | API_US05 | Bir yönetici olarak API baglantisi üzerinden id'si verilen kullanicinin Visitor Purpose bilgilerine erisebilmeliyim. | /api/visitorsPurposeId endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Huriye | Backend (API)
/api/visitorsPurposeId endpoint'ine gecersiz authorization bilgileri ve gecersiz data (id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki datalar(id,visitors_purpose,description,created_at) dogrulanmali.
/api/visitorsPurposeAdd | API_US06 | Bir yönetici olarak API baglantisi üzerinden yeni bir visitor purpose kaydi olusturabilmek istiyorum. | /api/visitorsPurposeAdd endpoint'ine gecerli authorization bilgileri ve dogru datalar (visitors_purpose, description) iceren bir POST body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Sariye | Backend (API)
/api/visitorsPurposeAdd endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (visitors_purpose, description) iceren bir POST body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
API uzerinden olusturulmak istenen yeni visitor purpose kaydinin olustugu API uzerinden dogrulanmali.
/api/visitorsPurposeUpdate | API_US07 | Bir yönetici olarak API baglantisi üzeriden sisteme kayitli visitor purpose bilgilerini guncelleyebilmeliyim. | /apihttps://www.heallifehospital.com endpoint'ine gecerli authorization bilgileri ve dogru datalar (id, visitors_purpose, description) iceren bir PATCH body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Sevilay | Backend (API)
/api/visitorsPurposeUpdate endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (id, visitors_purpose, description) iceren bir PATCH body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki updateId bilgisinin /api/visitorsPurposeUpdate endpoint'ine gönderilen patch request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden güncellenmek istenen visitor purpose kaydinin güncellendigi, API uzerinden dogrulanmali.
/api/visitorsPurposeDelete | API_US08 | Bir yönetici olarak API baglantisi üzerinden sistemdeki visitor puspose kaydini silebilmeliyim. | /api/visitorsPurposeDelete endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir DELETE body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/visitorsPurposeDelete endpoint'ine gecersiz authorization bilgileri veya yanlis data (id) iceren bir DELETE body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki DeletedId bilgisinin /api/visitorsPurposeDelete endpoint'ine gönderilen delete request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden silinmek istenen visitor purpose kaydinin silindigi, API uzerinden dogrulanmali.
/api/visitorsList | API_US09 | Bir yönetici olarak API baglantisi üzerinden Visitor List'e erisebilmeliyim. | /api/visitorsList endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  | Huseyin | Backend (API)
/api/visitorsList endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"38" olan icerigin source: "Online", purpose:"Improve local visibility for heallifehospital.com", name: "Mike Holmes", email: "no-replyAnnora@gmail.com" , date:"2023-05-16", created_at: "2023-05-15 21:24:47" oldugu) dogrulanmali.
/api/visitorsId | API_US10 | Bir yönetici olarak API baglantisi üzerinden id'si verilen kullanicinin Visitor bilgilerine erisebilmeliyim. | /api/visitorsId endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Ibrahim | Backend (API)
/api/visitorsId endpoint'ine gecersiz authorization bilgileri ve gecersiz data (id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki datalar (id, sources, purpose, name, email, contact, id_proof, visit_to, ipd_opd_staff_id, related_to, no_of_pepple, date, in_time, out_time, note, created_at) dogrulanmali.
/api/visitorsAdd | API_US11 | Bir yönetici olarak API baglantisi üzerinden yeni bir visitor kaydi olusturabilmek istiyorum. | /api/visitorsAdd endpoint'ine gecerli authorization bilgileri ve dogru datalar (purpose, name, email, contact, id_proof, visit_to, ipd_opd_staff_id, related_to, no_of_pepple, date, in_time, out_time, note) iceren bir POST body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Ersin | Backend (API)
/api/visitorsAdd endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (purpose, name, email, contact, id_proof, visit_to, ipd_opd_staff_id, related_to, no_of_pepple, date, in_time, out_time, note) iceren bir POST body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
API uzerinden olusturulmak istenen yeni visitor kaydinin olustugu, API uzerinden dogrulanmali.
/api/visitorsUpdate | API_US12 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli visitor bilgilerini guncelleyebilmeliyim. | /api/visitorsUpdate endpoint'ine gecerli authorization bilgileri ve dogru datalar (id, purpose, name, email, contact, id_proof, visit_to, ipd_opd_staff_id, releated_to, no_of_pepple, date, in_time, out_time, note) iceren bir PATCH body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Murat S | Backend (API)
/api/visitorsUpdate endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (id, purpose, name, email, contact, id_proof, visit_to, ipd_opd_staff_id, releated_to, no_of_pepple, date, in_time, out_time, note) iceren bir PATCH body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki updateId bilgisinin /api/visitorsUpdate endpoint'ine gönderilen patch request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden güncellenmek istenen visitor kaydinin güncellendigi, API uzerinden dogrulanmali.
/api/visitorsDelete | API_US13 | Bir yönetici olarak API baglantisi üzerinden sistemdeki visitor kaydini silebilmeliyim. | /api/visitorsDelete endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir DELETE body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/visitorsDelete endpoint'ine gecersiz authorization bilgileri veya yanlis data (id) iceren bir DELETE body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki DeletedId bilgisinin /api/visitorsDelete endpoint'ine gönderilen delete request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden silinmek istenen visitor kaydinin silindigi, API uzerinden dogrulanabilmeli.
/api/getBloodGroup | API_US14 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli kan grubu listesine erisebilmeliyim. | /api/getBloodGroup endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  |  | Backend (API)
/api/getBloodGroup endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"3" olan icerigin name: "AB-", is_blood_group: "1", created_at: "2021-10-25 02:32:41" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"8" olan icerigin name: "O+", is_blood_group: "1", created_at: "2021-10-25 02:33:28" oldugu) dogrulanmali.
/api/getBloodGroupById | API_US15 | Bir yönetici olarak API baglantisi üzerinden id girerek ilgili kan verilerine erisebilmeliyim. | /api/getBloodGroupById endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/getBloodGroupById endpoint'ine gecersiz authorization bilgileri ve gecersiz data (id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki datalar(id, name, is_blood_group, created_at) dogrulanmali.
/api/addBloodGroup | API_US16 | Bir yönetici olarak API baglantisi üzerinden yeni bir kan grubu olusturabilmek istiyorum. | /api/addBloodGroup endpoint'ine gecerli authorization bilgileri ve dogru datalar (name,is_blood_group) iceren bir POST body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Murat K | Backend (API)
/api/addBloodGroup endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (name,is_blood_group) iceren bir POST body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
API uzerinden olusturulmak istenen yeni kan grubu kaydinin olustugu, API uzerinden dogrulanmali.
/api/updateBloodGroup | API_US17 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli kan bilgilerini guncelleyebilmeliyim. | /api/updateBloodGroup endpoint'ine gecerli authorization bilgileri ve dogru datalar (id, name,is_blood_group) iceren bir PATCH body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Huseyin | Backend (API)
/api/updateBloodGroup endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (id, name,is_blood_group) iceren bir PATCH body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki updateId bilgisinin /api/updateBloodGroup endpoint'ine gönderilen patch request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden güncellenmek istenen kan grubu kaydinin güncellendigi API uzerinden dogrulanmali.
/api/deleteBloodGroup | API_US18 | Bir yönetici olarak API baglantisi üzerinden sistemdeki kan grubu kaydini silebilmeliyim. | /api/deleteBloodGroup endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir DELETE body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/deleteBloodGroup endpoint'ine gecersiz authorization bilgileri veya yanlis data (id) iceren bir DELETE body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki deletedId bilgisinin /api/deleteBloodGroup endpoint'ine gönderilen delete request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden silinmek istenen kan grubu kaydinin silindigi, API uzerinden dogrulanmali.
/api/getExpenseHead | API_US19 | Bir yönetici olarak API baglantisi üzerinden hastane masraflarina erisebilmeliyim. | /api/getExpenseHead endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  |  | Backend (API)
/api/getExpenseHead endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"5" olan icerigin exp_category: "Power Generator Fuel Charge", description: "They can utilise a variety of fuel options including natural gas, LPG and diesel.", is_active: "yes", is_deleted: "no", created_at: "2021-10-29 01:35:42" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"4" olan icerigin exp_category: "Telephone Bill", description: "Recently, some private insurance companies have begun to pay for patient-to-provider phone calls, especially when the calls are prolonged and when medical decisions are made. Nevertheless, you may be billed for the whole cost, or you may have to pay a co-pay.", is_active: "yes", is_deleted: "no", created_at: "2021-10-29 01:36:02" oldugu) dogrulanmali.
/api/getExpenseHeadById | API_US20 | Bir yönetici olarak API baglantisi üzerinden id girerek ilgili harcama verilerine erisebilmeliyim. | /api/getExpenseHeadById endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Murat S | Backend (API)
/api/getExpenseHeadById endpoint'ine gecersiz authorization bilgileri ve gecersiz data (id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki datalar (id, exp_category, description, is_active, is_deleted, created_at) dogrulanmali.
/api/addExpenseHead | API_US21 | Bir yönetici olarak API baglantisi üzerinden yeni bir harcama olusturabilmek istiyorum. | /api/addExpenseHead endpoint'ine gecerli authorization bilgileri ve dogru datalar (exp_category, description, is_active, is_deleted) iceren bir POST body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Huriye | Backend (API)
/api/addExpenseHead endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (exp_category, description, is_active, is_deleted) iceren bir POST body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
API uzerinden olusturulmak istenen yeni harcama kaydinin olustugu, API uzerinden dogrulanmali.
/api/updateExpenseHead | API_US22 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli harcama bilgilerini guncelleyebilmek istiyorum.. | /api/updateExpenseHead endpoint'ine gecerli authorization bilgileri ve dogru datalar (id, exp_category, description, is_active, is_deleted) iceren bir PATCH body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Ibrahim | Backend (API)
/api/updateExpenseHead endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (id, exp_category, description, is_active, is_deleted) iceren bir PATCH body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki updateId bilgisinin /api/updateExpenseHead endpoint'ine gönderilen patch request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden güncellenmek istenen harcama kaydinin güncellendigi, API uzerinden dogrulanmali.
/api/deleteExpenseHead | API_US23 | Bir yönetici olarak API baglantisi üzerinden sistemdeki harcama kaydini silebilmeliyim. | /api/deleteExpenseHead endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir DELETE body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/deleteExpenseHead endpoint'ine gecersiz authorization bilgileri veya yanlis data (id) iceren bir DELETE body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki deletedId bilgisinin /api/deleteExpenseHead endpoint'ine gönderilen delete request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden silinmek istenen harcama kaydinin silindigi, API uzerinden dogrulanmali.
/api/getNotice | API_US24 | Bir yönetici olarak API baglantisi üzerinden duyurulara erisebilmeliyim. | /api/getNotice endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  |  | Backend (API)
/api/getNotice endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"37" olan icerigin type: "notice", slug: "happy-30-march-medicine-day", url: "page/", title": "Happy 30 March Medicine Day", date: "2023-03-30", description": "<p><img align=\"left\" src=\"https://qa.heallifehospital.com/uploads/gallery/media/2.jpg\" width=\"300\" xss=\"removed\"></p>\r\n\r\n<p>On March 30th, we celebrate the contributions and hard work of the doctors in our hospital on International Medicine Day. This day is a time to acknowledge the crucial role that medicine plays in improving health and saving lives.</p>\r\n\r\n<p>Our theme for this year&#39;s celebration is \"Advancing Health Through Science and Technology\", highlighting the importance of investing in medical research and innovation. It is a day to appreciate the efforts of our healthcare professionals and researchers in developing innovative treatments and cures for various diseases.</p>\r\n\r\n<p>We would like to take this opportunity to extend our gratitude to all the doctors in our hospital for their tireless work and dedication to providing the best care to our patients. Your compassion, expertise, and commitment to advancing the field of medicine do not go unnoticed.</p>\r\n\r\n<p>Let&#39;s celebrate this day together and continue to support our healthcare professionals in their efforts to improve the lives of those around us. Happy March 30th Medicine Day!</p>", is_active: "no", oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"38" olan icerigin type: "notice", slug: "from-the-harvard-university-cell-science-course-prof-dr-alexander-smith-will-attend-the-cell-science-panel-to-be-held-in-our-hospital-as-a-speaker", url: "page/", title": "From the Harvard University Cell Science course. Prof. Dr. Alexander Smith will attend the Cell Science panel to be held in our hospital as a speaker.", date:"2023-05-10",, is_active: "no", oldugu) dogrulanmali.
/api/getNoticeById | API_US25 | Bir yönetici olarak API baglantisi üzerinden id girerek ilgili duyuru verisine erisebilmeliyim. | /api/getNoticeById endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Nurettin | Backend (API)
/api/getNoticeById endpoint'ine gecersiz authorization bilgileri ve gecersiz data (id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki datalar (id, type, slug, url, title, date, event_start, event_end, event_venue, description, is_active, created_at, meta_title, meta_description, meta_keyword, feature_image, publish_date, publish, sidebar) dogrulanmali.
/api/addNotice | API_US26 | Bir yönetici olarak API baglantisi üzerinden yeni bir duyuru kaydi olusturabilmek istiyorum. | /api/addNotice endpoint'ine gecerli authorization bilgileri ve dogru datalar (type, title, description, slug) iceren bir POST body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Nurettin | Backend (API)
/api/addNotice endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (type, title, description, slug) iceren bir POST body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
API uzerinden olusturulmak istenen yeni duyuru kaydinin olustugu, API uzerinden dogrulanmali.
/api/updateNotice | API_US27 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli duyuru bilgilerini guncelleyebilmeliyim. | /api/updateNotice endpoint'ine gecerli authorization bilgileri ve dogru datalar (id, type, title, description, slug) iceren bir PATCH body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/updateNotice endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (id, type, title, description, slug) iceren bir PATCH body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki updateId bilgisinin /api/updateNotice endpoint'ine gönderilen patch request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden güncellenmek istenen duyuru kaydinin güncellendigi, API uzerinden dogrulanmali.
/api/deleteNotice | API_US28 | Bir yönetici olarak API baglantisi üzerinden sistemdeki duyuru kaydini silebilmeliyim. | /api/deleteNotice endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir DELETE body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/deleteNotice endpoint'ine gecersiz authorization bilgileri veya yanlis data (id) iceren bir DELETE body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki deletedId bilgisinin /api/deleteNotice endpoint'ine gönderilen delete request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden silinmek istenen duyuru kaydinin silindigi API uzerinden dogrulanmali.
/api/getFindingCategory | API_US29 | Bir yönetici olarak API baglantisi üzerinden finding category listesine erisebilmeliyim. | /api/getFindingCategory endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  |  | Backend (API)
/api/getFindingCategory endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"1" olan icerigin category: "Fever", created_at: "2021-10-25 02:02:48" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"2" olan icerigin category: "Typhidot (or Widal Test)", created_at: "2021-10-25 02:03:35" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"3" olan icerigin category: "Skin Problem", created_at: "2021-10-25 02:14:41" oldugu) dogrulanmali.
/api/getFindingCategoryById | API_US30 | Bir yönetici olarak API baglantisi üzerinden id girerek ilgili finding category verisine erisebilmeliyim. | /api/getFindingCategoryById endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/getFindingCategoryById endpoint'ine gecersiz authorization bilgileri ve gecersiz data (id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki datalar(id, category, created_at) dogrulanmali.
/api/addFindingCategory | API_US31 | Bir yönetici olarak API baglantisi üzerinden yeni bir finding category kaydi olusturabilmek istiyorum. | /api/addFindingCategory endpoint'ine gecerli authorization bilgileri ve dogru datalar (category, created_at) iceren bir POST body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/addFindingCategory endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (category, created_at) iceren bir POST body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
API uzerinden olusturulmak istenen yeni finding category kaydinin olustugu, API uzerinden dogrulanmali.
/api/updateFindingCategory | API_US32 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli finding category bilgilerini guncelleyebilmeliyim. | /api/updateFindingCategory endpoint'ine gecerli authorization bilgileri ve dogru datalar (id,category) iceren bir PATCH body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/updateFindingCategory endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (id,category) iceren bir PATCH body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki updateId bilgisinin /api/updateFindingCategory endpoint'ine gönderilen patch request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden güncellenmek istenen finding category kaydinin güncellendigi, API uzerinden dogrulanmali.
/api/deleteFindingCategory | API_US33 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli finding category kaydini silebilmeliyim. | /api/deleteFindingCategory endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir DELETE body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/deleteFindingCategory endpoint'ine gecersiz authorization bilgileri veya yanlis data (id) iceren bir DELETE body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki deletedId bilgisinin /api/deleteFindingCategory endpoint'ine gönderilen delete request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden silinmek istenen finding category kaydinin silindigi API uzerinden dogrulanmali.
/api/getFinding | API_US34 | Bir yönetici olarak API baglantisi üzerinden finding listesine erisebilmeliyim. | /api/getFinding endpoint'ine gecerli authorization bilgileri ile bir GET request gönderildiginde dönen status code'un 200 oldugu ve response message bilgisinin "Success" oldugu dogrulanmali. |  |  |  | Backend (API)
/api/getFinding endpoint'ine gecersiz authorization bilgileri ile bir GET Request gönderildiginde dönen status code'un 403 oldugu ve response message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigi (id:"12" olan icerigin name: "Refractive Errors.", description: "A refractive error is a very common eye disorder. It occurs when the eye cannot clearly focus the images from the outside world. The result of refractive errors is blurred vision, which is sometimes so severe that it causes visual impairment", finding_category_id: "6", created_at: "2021-10-25 02:20:29", category: "Eye Diseases" oldugu) dogrulanmali.
Response body icindeki list icerigi (id:"7" olan icerigin name: "Rosacea.", description: "Rosacea (roe-ZAY-she-uh) is a common skin condition that causes blushing or flushing and visible blood vessels in your face. It may also produce small, pus-filled bumps. These signs and symptoms may flare up for weeks to months and then go away for a while.", finding_category_id: "3", created_at: "2021-10-25 02:15:36", category: "Skin Problem" oldugu) dogrulanmali.
/api/getFindingById | API_US35 | Bir yönetici olarak API baglantisi üzerinden id girerek ilgili finding verisine erisebilmeliyim. | /api/getFindingById endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/getFindingById endpoint'ine gecersiz authorization bilgileri ve gecersiz data (id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki datalar (id, name, description, finding_category_id, created_at, category) dogrulanmali.
/api/getFindingCategoryId | API_US36 | Bir yönetici olarak API baglantisi üzerinden id girerek ilgili finding category verilerine erisebilmeliyim. | /api/getFindingCategoryId endpoint'ine gecerli authorization bilgileri ve dogru data (finding_category_id) iceren bir GET body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/getFindingCategoryId endpoint'ine gecersiz authorization bilgileri ve gecersiz data(finding_category_id) iceren bir GET body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki list icerigindeki veriler (id, name, description, finding_category_id, created_at bilgileri ile) dogrulanmali.
/api/addFinding | API_US37 | Bir yönetici olarak API baglantisi üzerinden yeni bir finding kaydi olusturabilmek istiyorum. | /api/addFinding endpoint'ine gecerli authorization bilgileri ve dogru datalar (name, description, finding_category_id) iceren bir POST body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Sevilay | Backend (API)
|  |  | /api/addFinding endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (name, description, finding_category_id) iceren bir POST body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali |  |  |  |  | [API_US16]
API uzerinden olusturulmak istenen yeni finding kaydinin olustugu, API uzerinden dogrulanmali.
/api/updateFinding | API_US38 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli finding bilgilerini guncelleyebilmeliyim. | /api/updateFinding endpoint'ine gecerli authorization bilgileri ve dogru datalar (id,name,description,finding_category_id ) iceren bir PATCH body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  | Sariye | Backend (API)
/api/updateFinding endpoint'ine gecersiz authorization bilgileri veya yanlis datalar (id,name,description,finding_category_id ) iceren bir PATCH body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki updateId bilgisinin /api/updateFinding endpoint'ine gönderilen patch request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden güncellenmek istenen finding kaydinin güncellendigi, API uzerinden dogrulanmali.
/api/deleteFinding | API_US39 | Bir yönetici olarak API baglantisi üzerinden sisteme kayitli finding kaydini silebilmeliyim. | /api/deleteFinding endpoint'ine gecerli authorization bilgileri ve dogru data (id) iceren bir DELETE body gönderildiginde dönen status code'in 200 oldugu ve response body'deki message bilgisinin "Success" oldugu dogrulanmali |  |  |  | Backend (API)
/api/deleteFinding endpoint'ine gecersiz authorization bilgileri veya yanlis data (id) iceren bir DELETE body gönderildiginde dönen status code'in 403 oldugu ve response body'deki message bilgisinin "failed" oldugu dogrulanmali
Response body icindeki deletedId bilgisinin /api/deleteFinding endpoint'ine gönderilen delete request body icindeki id bilgisi ile ayni oldugu dogrulanmali.
API uzerinden silinmek istenen finding kaydinin silindigi API uzerinden dogrulanmali.

## API -> Admin_Access
admin |  | Password | Postman Documantation
selman.karakoc | selman.karakoc.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
hatice.kubra.ceylan | hatice.kubra.ceylan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
mustafa.culha | mustafa.culha.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
erhan.ciftci | erhan.ciftci.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sevilay.turkoglu | sevilay.turkoglu.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ilyas.u | ilyas.u.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
abdullah.ak | abdullah.ak.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
yusuf.kombe | yusuf.kombe.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
emine.bas | emine.bas.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ferit.ocal | ferit.ocal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
furkan.veli.inal | furkan.veli.inal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
mehmet.harun.apak | mehmet.harun.apak.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ahmet.bicakci | ahmet.bicakci.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
berkan.sonmezay | berkan.sonmezay.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
hasan.korpe | hasan.korpe.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ahmet.emre.elieyioğlu | ahmet.emre.elieyioğlu.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
muhammed.furkan.kocer | muhammed.furkan.kocer.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ragip.ozata | ragip.ozata.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ali.tozcu | ali.tozcu.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
kubra.ercin | kubra.ercin.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
esra.unal | esra.unal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
murat.sever | murat.sever.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
huriye.sever | huriye.sever.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
eyup.ortatepe | eyup.ortatepe.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ayse.nuriye.alcik | ayse.nuriye.alcik.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
mehmet.dag | mehmet.dag.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
tugba.gokce | tugba.gokce.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
fidan.parlak | fidan.parlak.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
miyase.colak | miyase.colak.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sariye.yucel | sariye.yucel.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
azat.ozay | azat.ozay.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
inci.cakmak | inci.cakmak.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
umre.aslan | umre.aslan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
hakan.cakir | hakan.cakir.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
fazilet.betul.alptekin | fazilet.betul.alptekin.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
emre.karakullukcu | emre.karakullukcu.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
tuna.akgumus | tuna.akgumus.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
bektas.alakus | bektas.alakus.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
betul.ahlatci | betul.ahlatci.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
zafer.sahingoz | zafer.sahingoz.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sevim.yigit | sevim.yigit.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
humeyra.uysal | humeyra.uysal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
elif.isci | elif.isci.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
serife.oral | serife.oral.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
mehmet.erden | mehmet.erden.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
neslihan.yildiz | neslihan.yildiz.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
harun.cigci | harun.cigci.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ayten.kok | ayten.kok.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
gurkan.gulsoy | gurkan.gulsoy.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
said.ozkan | said.ozkan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
belkis.oruc | belkis.oruc.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
talha.duman | talha.duman.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
hamza.cicek | hamza.cicek.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ahmet.yazicioglu | ahmet.yazicioglu.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
tolga.gundal | tolga.gundal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sumeyra.capar | sumeyra.capar.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ahmet.dogan | ahmet.dogan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
hasan.adiguzel | hasan.adiguzel.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
tugba.fidan | tugba.fidan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
huseyin.emre.senol | huseyin.emre.senol.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
nesibe.unal | nesibe.unal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
berivan.gencdal | berivan.gencdal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sinan.sheydayev | sinan.sheydayev.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
enver.kuris | enver.kuris.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ramazan.ay | ramazan.ay.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
mehmet.meral | mehmet.meral.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ali.mat | ali.mat.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ayse.busra.pehlivan | ayse.busra.pehlivan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
burhan.tastan | burhan.tastan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
havva.gokkaya | havva.gokkaya.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ersin.karapazarlioglu | ersin.karapazarlioglu.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
gulhayat.guder | gulhayat.guder.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
mahmut.coskun | mahmut.coskun.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
mahmut.yatak | mahmut.yatak.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sumeyye.alakabak | sumeyye.alakabak.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
hasan.sen | hasan.sen.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
erman.coskun | erman.coskun.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
zehranur.avcibasi | zehranur.avcibasi.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
murat.korkmaz | murat.korkmaz.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
duygu.gunaydin | duygu.gunaydin.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
huseyin.sen | huseyin.sen.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
taha.ozerler | taha.ozerler.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
muhammet.lutfi.erdem | muhammet.lutfi.erdem.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
berrin.demir | berrin.demir.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sadettin.akman | sadettin.akman.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
seher.caluk | seher.caluk.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
huri.yilmaz | huri.yilmaz.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
sevgi.yildirim | sevgi.yildirim.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
esra.turker | esra.turker.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
tahir.karayer | tahir.karayer .admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
muhammed.cenab.koroglu | muhammed.cenab.koroglu .admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
vahit.akpinar | vahit.akpinar .admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
abdullah.ak | abdullah.ak .admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
rana.ozkan | rana.ozkan.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ahmetsenturk | ahmetsenturk.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
fatihkent | fatihkent.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ibrahimkavakli | ibrahimkavakli.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
nurettinkoca | nurettinkoca.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
ozancalisal | ozancalisal.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm
turkergoksin | turkergoksin.admin@heallifehospital.com | heallife123 | https://documenter.getpostman.com/view/25004583/2s93m33Npm

## DB Product Backlog(Turkish)
DB US
US_ID | Table Name | Description | Priority | Point | Assigne | TEST TYPE
DB_US01 | heallife_hospitaltraining.ambulance_call | Database üzerinden ambulance_call tablosundaki patient_id = 1 olan hastanin driver'i Smith olan ambulance ile 2 defa sevkinin gerceklestigini dogrulayiniz |  |  | Huriye | Backend (Database)
DB_US02 | heallife_hospitaltraining.appointment | Database üzerinden hastane sistemine gerekli bilgiler girilerek randevu alinabildigini dogrulayiniz. |  |  | Murat S | Backend (Database)
DB_US03 | heallife_hospitaltraining.appointment | Database üzerinden appointment tablosundaki patient_id = 20 olan hastanin canli muayene isteginin acik oldugunu dogrulayiniz. |  |  | Ibrahim | Backend (Database)
DB_US04 | heallife_hospitaltraining.appointment | Database üzerinden appointment tablosunda ögleden önce icin alinmis randevularin ögleden sonra icin alinan randevulardan az oldugunu dogrulayiniz. |  |  | Sariye | Backend (Database)
DB_US05 | heallife_hospitaltraining.appointment_payment | Database üzerinden appointment_payment tablosunda odeme turu olarak "offline" secenl hasta id'lerinin (1,2,3,16,17,18,20,21,24,25,31) oldugunu dogrulayiniz. |  |  | Sevilay | Backend (Database)
DB_US06 | heallife_hospitaltraining.appointment_queue | Database üzerinden appointment_queue tablosunda 2023 yilinda olusturulan iceriklerden mayis ayinda olusturulanlari listeleyip dogrulayiniz. |  |  | Ersin | Backend (Database)
DB_US07 | heallife_hospitaltraining.bed | Database uzerinden bed tablosunda created_at = 2021-10-25 03:34:25 olan yatagin active oldugunu dogrulayiniz. |  |  | Huseyin | Backend (Database)
DB_US08 | heallife_hospitaltraining.bed | Database üzerinden bed tablosunda bed group id'si 4 ve is_active= "no" olan hastanin name bilgisinin 105 oldugunu dogrulayiniz. |  |  | Murat K | Backend (Database)
DB_US09 | heallife_hospitaltraining.birth_report | Database üzerinden birth_report tablosunda agirligi 2,5 kg ve ustu olan bebek sayisinin 6 oldugunu dogrulayiniz. |  |  | Nurettin | Backend (Database)
DB_US10 | heallife_hospitaltraining.birth_report | Database üzerinden birth_report tablosunda kardes olan bebekleri listeleyip isimlerini dogrulayiniz. |  |  | Huriye | Backend (Database)
DB_US11 | heallife_hospitaltraining.blood_donor | Database üzerinden blood_donor tablosundaki id= 7 olan donorun donor_name'i Maria, date_of_birth=2001-03-02, gender=Female, father_name=Jhonson, address=England oldugunu dogrulayiniz. |  |  | Murat S | Backend (Database)
DB_US12 | heallife_hospitaltraining.blood_donor_cycle | Databese üzerinden blood_donor_cycle tablosundaki institution'i belli olan id numaralarini listeleyiniz. Ve listede id=17 oldugunu dogrulayiniz. |  |  | Ibrahim | Backend (Database)
DB_US13 | heallife_hospitaltraining.charge_categories | Database uzerinden charge_categories tablosundaki name bilgisi "P" ile baslayan iceriklerin charge_type_id numaralarini tekrardan arindirilmis olarak listeleyiniz ve dogrulayiniz. (6 , 7) |  |  | Sariye | Backend (Database)
DB_US14 | heallife_hospitaltraining.charges | Database üzerinden charges tablosundaki verileri kucukten buyuge dogru siralayip ilk 5 tanesinin (100, 100,100,110,120 oldugunu) dogrulayiniz. |  |  | Sevilay | Backend (Database)
DB_US15 | heallife_hospitaltraining.consultant_register | Database üzerinden consultant_register tablosuna yeni bir kayit eklenebildigi dogrulanmali. |  |  | Ersin | Backend (Database)
DB_US16 | heallife_hospitaltraining.death_report | Database üzerinden death_report tablosundaki ölüm tarihlerine göre en son ölen hastanin guardian_name bilgisinin Kane Stark oldugunu dogrulayiniz. |  |  | Huseyin | Backend (Database)
DB_US17 | heallife_hospitaltraining.department | Database üzerinden department tablosundaki iceriklerin department_name ve created_at bilgilerinin eslestigi dogrulanmali. |  |  | Murat K | Backend (Database)
DB_US18 | heallife_hospitaltraining.discharge_card | Database üzerinden discharge_card tablosundaki opd_details_id'si 11 ile 31 arasindaki (11 ve 31 haric) verlerin created_at bilgilerini dogrulayiniz. |  |  | Nurettin | Backend (Database)
DB_US19 | heallife_hospitaltraining.doctor_shift | Database üzerinden doctor_shift tablosunda staff_id=2 olan doctorun sali gunu kac saat calistigini dgorulayiniz. (2) |  |  | Huriye | Backend (Database)
DB_US20 | heallife_hospitaltraining.events | Database üzerinden events tablosundan veri silinebildigini dogrulayiniz. |  |  | Murat S | Backend (Database)
DB_US21 | heallife_hospitaltraining.lab | Database üzerinden lab tablosundaki laboratuarlardan X-RAY laboratuarlarinin id lerini listeleyiniz. Id lerden en buyugunun (3 oldugunu) dogrulayiniz. |  |  | Ibrahim | Backend (Database)
DB_US22 | heallife_hospitaltraining.languages | Database üzerinden languages tablosundaki short_code "yi" olan verinin language bilgisinin "Yiddish" oldugunu dogrulayin. |  |  | Sariye | Backend (Database)
DB_US23 | heallife_hospitaltraining.medicine_supplier | Database üzerinden medicine_supplier tablosundaki address bilgisi "Andheri, Mumbai" olan verinin diger bilgilerinin dogru oldugunu kontrol ediniz. |  |  | Sevilay | Backend (Database)
DB_US24 | heallife_hospitaltraining.nurse_note | Database üzerinden nurse_note tablosuna coklu veri girisi yapilabildigi dogrulanmali. |  |  | Ersin | Backend (Database)
DB_US25 | heallife_hospitaltraining.patients | Database üzerinden patients tablosundaki patient_name bilgisi "Jain" iceren hastalarin gender ve email bilgilerini dogrulayiniz. |  |  | Huseyin | Backend (Database)
DB_US26 | heallife_hospitaltraining.patients | Database üzerinden patients tablosundaki en eski hastanin known_allergies bilgisinin "Fast food" oldugunu dogrulayin. |  |  | Murat K | Backend (Database)
DB_US27 | heallife_hospitaltraining.staff | Database üzerinden staff tablosundaki qualification=MS, specialization= Neurology olan iceriklerin account_title verilerini harf sirasina göre siralayarak listeyiniz. |  |  | Nurettin | Backend (Database)
DB_US28 | heallife_hospitaltraining.vehicles | Database üzerinden vehicles tablosundaki en eski aracin driver_name=bayram erguven ve driver_licence =b oldugunu dogrulayiniz. |  |  |  | Backend (Database)
DB_US29 | heallife_hospitaltraining.vehicles | Database üzerinden vehicles tablosundaki araclarin manufacture_year bilgisine göre en eskiden yeniye listelendiginde ve created_at bilgisine görede eskiden yeniye siralanip listelendiginde iki listede de ayni indexte yer alan arac oldugunu dogrulayiniz. |  |  |  | Backend (Database)
DB_US30 | heallife_hospitaltraining.visitors_book | Database üzerinden visitors_book tablosundaki verilerden Maria Fernandis'i ziyarete gelen ziyaretcinin isminin Jhon oldugunu dogrulayiniz. |  |  |  | Backend (Database)
TEST DATALARI
DB_US06 |  | 13 59 2 1 18 2023-05-04 2023-05-04 05:43:13 14 57 2 2 18 2023-05-04 2023-05-04 05:43:13 15 58 2 3 18 2023-05-04 2023-05-04 05:43:13 16 54 2 4 18 2023-05-04 2023-05-04 05:43:13
DB_US10 |  | Rohit, Reyana, child
DB_US18 |  | 2021-10-28 04:49
2023-05-03 13:35
DB_US23 |  | 3 | VKS Pharmacy | 7546985214 | Vinay Shrivastava | 9754632587 | DFDR555--000 | Andheri, Mumbai | 2021-10-25 03:09
DB_US25 |  | reshu@gmail.com | Female
|  | umair@gmail.com | Male

## DB Product Backlog(English)
DB US
US_ID | Table Name | Description | priority | point | Assigne | TEST TYPE
DB_US01 | heallife_hospitaltraining.ambulance_call | Verify that the patient with patient_id = 1 in the ambulance call table on the database has been dispatched 2 times by the ambulance whose driver is Smith. |  |  | Huriye | Backend (Database)
DB_US02 | heallife_hospitaltraining.appointment | Verify that an appointment can be made by entering the necessary information into the hospital system via the database. |  |  | Murat S | Backend (Database)
DB_US03 | heallife_hospitaltraining.appointment | Verify that the live examination request of the patient with patient_id = 20 in the appointment table on the database is open. |  |  | Ibrahim | Backend (Database)
DB_US04 | heallife_hospitaltraining.appointment | In the appointment table on the database, verify that the appointments made for the morning are less than the appointments for the afternoon. |  |  | Sariye | Backend (Database)
DB_US05 | heallife_hospitaltraining.appointment_payment | In the appointment_payment table through the database, verify that the patient IDs selected as "offline" as the payment type are: (1,2,3,16,17,18,20,21,24,25,31). |  |  | Sevilay | Backend (Database)
DB_US06 | heallife_hospitaltraining.appointment_queue | List and verify the contents created in 2023 in the appointment_queue table on the database, which were created in May. |  |  | Ersin | Backend (Database)
DB_US07 | heallife_hospitaltraining.bed | Verify that the bed with created_at = 2021-10-25 03:34:25 in the bed table from the database is active. |  |  | Huseyin | Backend (Database)
[TC_02->DB_US_018]
DB_US08 | heallife_hospitaltraining.bed | Verify that the name of the patient whose bed group id is 4 and is_active= "no" in the bed table on the database is 105. |  |  | Murat K | Backend (Database)
DB_US09 | heallife_hospitaltraining.birth_report | Verify that the number of babies with a weight of 2.5 kg and above is 6 in the birth_report table on the database. |  |  | Nurettin | Backend (Database)
DB_US10 | heallife_hospitaltraining.birth_report | List the sibling babies in the birth_report table on the database and verify their names. |  |  | Huriye | Backend (Database)
DB_US11 | heallife_hospitaltraining.blood_donor | Verify on the database that the donor_name of the donor with id= 7 in the blood_donor table is Maria, date_of_birth=2001-03-02, gender=Female, father_name=Jhonson, address=England. |  |  | Murat S | Backend (Database)
DB_US12 | heallife_hospitaltraining.blood_donor_cycle | List the id numbers whose institution is certain in the blood_donor_cycle table via Databese. And verify that id=17 is in the list. |  |  | Ibrahim | Backend (Database)
DB_US13 | heallife_hospitaltraining.charge_categories | List and verify the charge_type_id numbers of the contents whose name information starts with "P" in the charge_categories table over the database, without repetition. (6 , 7) |  |  | Sariye | Backend (Database)
DB_US14 | heallife_hospitaltraining.charges | Sort the data in the charges table via the database from smallest to largest, and verify the first 5 (100, 100,100,110,120). |  |  | Sevilay | Backend (Database)
DB_US15 | heallife_hospitaltraining.consultant_register | It should be verified that a new record can be added to the consultant_register table via the database. |  |  | Ersin | Backend (Database)
DB_US16 | heallife_hospitaltraining.death_report | Verify that the guardian_name of the last deceased patient is Kane Stark, according to the death dates in the death_report table via the database. |  |  | Huseyin | Backend (Database)
DB_US17 | heallife_hospitaltraining.department | It should be verified that the department_name and created_at information of the contents in the department table via the database match. |  |  | Murat K | Backend (Database)
DB_US18 | heallife_hospitaltraining.discharge_card | Verify the created_at information of the data with opd_details_id between 11 and 31 (except 11 and 31) in the discharge_card table over the database. |  |  | Nurettin | Backend (Database)
DB_US19 | heallife_hospitaltraining.doctor_shift | From the database, calculate how many hours the doctor with staff_id=2 in the doctor_shift table works on Tuesday. (2) |  |  | Huriye | Backend (Database)
DB_US20 | heallife_hospitaltraining.events | Verify that data can be deleted from the events table via the database. |  |  | Murat S | Backend (Database)
DB_US21 | heallife_hospitaltraining.lab | List the IDs of the X-RAY laboratories from the laboratories in the lab table. Verify that the largest of the ids is (3) by the database. |  |  | Ibrahim | Backend (Database)
DB_US22 | heallife_hospitaltraining.languages | Verify that the language information of the data whose short_code is "yi" in the languages table is "Yiddish" through the database. |  |  | Sariye | Backend (Database)
DB_US23 | heallife_hospitaltraining.medicine_supplier | Check that the other information of the data whose address information is "Andheri, Mumbai" in the medicine_supplier table on the database is correct. |  |  | Sevilay | Backend (Database)
DB_US24 | heallife_hospitaltraining.nurse_note | It should be verified that multiple data entries can be made to the nurse_note table through the database. |  |  | Ersin | Backend (Database)
DB_US25 | heallife_hospitaltraining.patients | Verify the gender and email information of the patients whose patient_name information contains "Jain" in the patients table on the database. |  |  | Huseyin | Backend (Database)
DB_US26 | heallife_hospitaltraining.patients | Verify that the oldest patient's known_allergies in the patients table from the database is "Fast food". |  |  | Murat K | Backend (Database)
DB_US27 | heallife_hospitaltraining.staff | List the account_title data of the contents with qualification=MS, specialization= Neurology in the staff table through the database by ordering them in alphabetical order. |  |  | Nurettin | Backend (Database)
DB_US28 | heallife_hospitaltraining.vehicles | Verify through the database that the oldest vehicle in the vehicles table is driver_name=bayram erguven and driver_licence =b. |  |  |  | Backend (Database)
DB_US29 | heallife_hospitaltraining.vehicles | Verify that when the vehicles in the vehicles table are listed from the oldest to the newest according to the manufacture_year information through the database, and the vehicles in the same index are listed in the same list according to the created_at information. |  |  |  | Backend (Database)
DB_US30 | heallife_hospitaltraining.visitors_book | Verify that the name of the visitor who came to visit Maria Fernandis from the data in the visitors_book table on the database is Jhon. |  |  |  | Backend (Database)
TEST DATA
DB_US06 |  | 13 59 2 1 18 2023-05-04 2023-05-04 05:43:13 14 57 2 2 18 2023-05-04 2023-05-04 05:43:13 15 58 2 3 18 2023-05-04 2023-05-04 05:43:13 16 54 2 4 18 2023-05-04 2023-05-04 05:43:13
DB_US10 |  | Rohit, Reyana, child
DB_US18 |  | 2021-10-28 04:49
|  | 2023-05-03 13:35 |  |  | Vinay Shrivastava
DB_US23 |  | 3 | VKS Pharmacy | 7546985214 |  | 9754632587 | DFDR555--000 | Andheri, Mumbai | 2021-10-25 03:09
DB_US25 |  | reshu@gmail.com | Female
|  | umair@gmail.com | Male

## DB-> Access Information
Heal Life Hospital Database Access Information
Connection name | jdbc:mysql
host/ip | 194140198209
port | 3306
database_name | heallife_hospitaltraining
username | heallife_hospitaltraininguser
password | 194.140.198.209
URL: "jdbc:mysql://194.140.198.209/heallife_hospitaltraining";
USERNAME= "heallife_hospitaltraininguser";
PASSWORD="PI2ZJx@9m^)3";